## 3 Alpha Sprint
List | Title | Description | Points | Due | Members | Labels | Card # | Card URL
Important Notes | Milestone Review | Not having a working build pushed to the milestone builds folder of the repo before the day of the milestone review is unacceptable. - All teams must have a zipped exe build in the “Milestone builds” folder - We aren’t working on user stories during class time on the day of the milestone - We aren’t integrating the builds during class time on the day of the milestone Previous sprint review - Finalize Trello board - - All user stories in final categories - - Hours spent on all tasks entered - Discus work problems if there were any - - If a user story estimate was off why was it off? Next sprint planning - Sprint goal must be understood - User stories moved from product backlog to sprint backlog that supports the sprint goal - Test cases and task lists reviewed for all sprint user stories Story allocation - Planning poker completed for all stories - User story owners assigned for all stories - Sprint plan reviewed and accepted by CD before the end of the lab It is Highly suggested that the team perform a code freeze no later then 4 hours before the milestone needs to be submitted. Code freeze: A time where no changes whatsoever are permitted to the program's source code used to maintain ensure the quality and integrity of the build. - Before each milestone and sprint end, a final integration is needed. - - Forces an integration at a safe time - - Ensures there is time for testing and validation of the build - - Confirm sprint goals - - Peer check each other’s work |  | 2022-10-10 23:59 |  |  | 1 | https://trello.com/c/LiTecV5l
Important Notes | Team's agreed upon schedule | The team should agree upon a schedule when and where they will be meeting up outside of class time and document those times and places onto this card. |  |  |  |  | 4 | https://trello.com/c/tPy4ohRz
Partially Complete | Eversor (Boss, Cave) | This will be the boss in the caves |  |  | K | Easy | 33 | https://trello.com/c/U2ZOd85F
Partially Complete | MiniMap | HUD map that shows surrounding terrain, player position and the location of the next quest. |  |  | KR | Moderate,Prereq: Quest system | 25 | https://trello.com/c/M8ptXz1B
Partially Complete | Castle | Building for final boss scene. Located in the royal city |  |  | L | Hard | 1 | https://trello.com/c/jSgfUTNW
Partially Complete | Bandit (Ranged) | Enemy - Ranged Bandit that uses magic |  |  | L | Moderate,Prereq: Powers | 42 | https://trello.com/c/PCEa70QH
Partially Complete | Soldier (Ranged) | Enemy - Ranged Soldier that uses magic |  |  | L | Moderate,Prereq: Powers | 39 | https://trello.com/c/2J7cS2T0
Partially Complete | Dialog / Quest System | Have a simple dialog / quest system in order to guide player to next objective/location |  |  | R | Hard | 49 | https://trello.com/c/sq8mBkxn
Partially Complete | Save System | Player will save current progress and be spawned from last point |  |  | R | Moderate | 38 | https://trello.com/c/WxvwqQii
Partially Complete | Wizard Boss | The wizard boss fight and all it's functionalities. |  |  | L | yellow | 55 | https://trello.com/c/q8V3XndY
Complete (Done) | Ice Power - Player | Raise ice spikes from the ground to attack enemies. |  |  | AL | Hard | 14 | https://trello.com/c/HTN4tpEL
Complete (Done) | Showcase Level | A level that can be loaded with a debug menu button or debug key check that shows all of the created features in sequence. This would not be a level the users would ever see, just a space that proves the functionality works in an easily accessible way. This will be removed later for the final builds. |  |  | KR,AL,K,L,R |  | 13 | https://trello.com/c/wjFOExoS
Complete (Done) | Completion scenario (winning the game, achieving achievements, high score) | Intent: - Create the win condition and all of the experience we intend to provide with it Notes on estimation: - Creating the trigger for a win screen is very fast and easy, presenting the actual win scenario of the game can vary in difficulty and time necessary based on how what will be done when the player wins |  |  | R |  | 2 | https://trello.com/c/l0Dh194J
Complete (Done) | Soldier (Melee) | Enemy - Melee Soldier that uses sword and shield |  |  | L,K | Moderate | 41 | https://trello.com/c/XooLvjEI
Complete (Done) | Keyboard and mouse for the game's menus | Intent: - Create control structure allowing keyboard and mouse to be used for all of the game's menus Note on estimation: - Using the unity input system this should be very quick to accomplish if it hasn't been already. |  |  | KR | TRC Requirement | 8 | https://trello.com/c/1k52fJEo
Complete (Done) | No warnings or errors in the code base | Intent: - Remove all warnings and errors from the product Note on estimation: - This is mostly a verification at the end of the sprint and usually needs little if any time dedicated to it unless there are currently known issues. People should be fixing warnings and errors as they develop their tasks. |  |  | KR | TRC Requirement | 6 | https://trello.com/c/xxQcxMn4
Complete (Done) | Ice Spike - Enemy | Main attack shoots ice spikes out of the ground beneath the player, bouncing them into the air if hit |  |  | AL | Easy,prereq: Knockback | 19 | https://trello.com/c/K4DWJXBS
Complete (Done) | Change options in the game | Intent: - Allow the end users to change the settings for music and SFX volume Note on implementation: - The easiest way to implement this is through setting up mixer groups and then routing the various audio sources in the game through the right mixer group (https://docs.unity3d.com/Manual/AudioMixer.html). An issue from mixer groups though is that they take volume in Db rather than a scaler 0 to 1 so it has to be converted. To roughly convert from a scaler value of 0-1 into logarithmic value for the unity mixer group is to use "Mathf.Log10(volume) * 20" Note on estimation: - Creating the menu doesn't take long. the difficulty and time involved on this one is in getting the mixer groups integrated in all of the audio sources in the game |  |  | KR | TRC Requirement | 5 | https://trello.com/c/irBEpF7q
Complete (Done) | Lightning Power | A blast of electricity between the caster and target as a texture that deals damage to enemy |  |  | KR | Moderate | 13 | https://trello.com/c/XnzQ3RAA
Complete (Done) | Compass | HUD compass to show which direction the player is walking |  |  | KR | Moderate,Prereq: Quest system | 26 | https://trello.com/c/3lt8p8jL
Complete (Done) | Lightning Power | A blast of electricity between the caster and target, Spider |  |  | KR | Moderate | 20 | https://trello.com/c/egcTcFOw
Complete (Done) | Enemy Knockback | Enemy knocked back by player attacks. |  |  | AL | Moderate | 17 | https://trello.com/c/iCuBHfti
Complete (Done) | Weapon Select | Switch between sword and spells (like we did with guns) |  |  | L | Easy | 15 | https://trello.com/c/N18c25G7
Complete (Done) | Loss condition and it is clear to the user when and how they lost | Intent: - Create loss condition and player feedback involved in it |  |  | R |  | 3 | https://trello.com/c/HLQi6NSn
Complete (Done) | Fire Ball | Main attack is a fire ball. Wolf |  |  | L | Easy,prereq: Knockback | 18 | https://trello.com/c/KsVtbRj3
Complete (Done) | Audio feedback on the menus | Intent: - Inform the user that the input was entered |  |  | KR | TRC Requirement | 11 | https://trello.com/c/0gkA5jgu
Complete (Done) | Health Bar | Will display the players current health, displaying green for what they have and red for what they lost. |  |  |  | Easy | 35 | https://trello.com/c/ZSahCtgB
Complete (Done) | Background music for the menus and levels | Intent: - Create ambiance and emotional tone for the game and levels. |  |  | R | TRC Requirement | 12 | https://trello.com/c/82oJDT2o
Complete (Done) | Royal City | The royal city outside the castle |  |  | AL | Easy | 37 | https://trello.com/c/hSWtOnN0
Complete (Done) | Game HUD | This will display information to the player of the current stats. Health, power/energy level and quests. |  |  | KR | Easy,Health bar, Boss health bar, power cool down | 34 | https://trello.com/c/jXL44bPn
Complete (Done) | Boss Health Bar | Will be used to indicate how much health the boss has left. |  |  |  | Easy | 36 | https://trello.com/c/Ms3XbL06
Complete (Done) | Camera | 3rd person camera view |  |  | KR | yellow | 40 | https://trello.com/c/OicvFQBW
Complete (Done) | Sprinting Animation | Animation the character will have when sprinting, moving. The animation will show the direction the character is move so position and orientation is known. |  |  | KR | Easy | 8 | https://trello.com/c/jm6SauwK
Complete (Done) | Jump Animation | Player will be able to jump and can only jump two times before having to land again. Animation will show what the character is doing. |  |  | KR | Easy | 7 | https://trello.com/c/UytShVhQ
Complete (Done) | Pause Menu | Will be used to pause the game so players can take a break from the challenge. Will have resume, quit and settings menu. All features will be pause in the current state. |  |  | K,KR | Easy,prereq: setting | 27 | https://trello.com/c/hQJSLXW5
Complete (Done) | Fire Power | A fiery projectile that explodes on impact and deal enemy damage |  |  | KR | Easy | 12 | https://trello.com/c/8ufdXXbI
Complete (Done) | Soldier & Bandit Art/Animation | Animation for movement and attacking |  |  | KR,K | Easy | 46 | https://trello.com/c/GFyVzJN0
Complete (Done) | Spider Art/Animation | The character model, animations, and sounds. |  |  | K | Easy | 48 | https://trello.com/c/dP1HfzpD
Complete (Done) | Cave1 | First cave the player encounters. Spider den |  |  | AL | Easy,prereq: background images | 4 | https://trello.com/c/SV9zGspu
Complete (Done) | Wolf Art/Animation | The character model, animations, and sounds. |  |  | K | Easy | 47 | https://trello.com/c/aN2gwo7b
Complete (Done) | Bandit (Melee) | Enemy - Melee Bandit that uses a sword |  |  | L,K | Moderate | 43 | https://trello.com/c/wSTTOhBq
Complete (Done) | Player Knockback | Apply knockback functionality to enemy attacks. |  |  | AL | Moderate | 22 | https://trello.com/c/95pShANk
Complete (Done) | Wolf - Functionality | Character functionality and movement. |  |  | K | Easy | 44 | https://trello.com/c/QEZRAUTc
Complete (Done) | Spider - Functionality | Character functionality and movement. |  |  | K | Easy | 45 | https://trello.com/c/muMasplL
Complete (Done) | Sword | Sword functionality |  |  | KR | Moderate | 16 | https://trello.com/c/lhwTJqgw
Complete (Done) | Base Implementation of Character movement | Basic movement, Player will be able to move left, right, jump and crouch. Animation of character must match what the character is doing. |  |  |  | Easy | 6 | https://trello.com/c/h6j7945I
Complete (Done) | Keyboard and mouse in-game | Intent: - Set up, test and use the default game controls for keyboard and mouse Note on estimation: - Using the unity input system this should be very quick to accomplish if it hasn't been already. |  |  | KR,L,K | TRC Requirement | 10 | https://trello.com/c/1daufxcB
Complete (Done) | Health / Mana Pick up | Intent: - An item that adds health to the player when picked up |  |  | AL | Easy | 24 | https://trello.com/c/q2WJOQf7
Complete (Done) | Navigate the main menu | Intent: - Create functionality for the main menu Note on estimation: - This is generally a very quick task since it is just the functionality of the menu (not final visuals) |  |  | KR | TRC Requirement,Prereq: Options menu/settings menu | 9 | https://trello.com/c/7yT7m2hB
Complete (Done) | Home Village | This is the player's home village. |  |  | AL | Easy,prereq: background images | 29 | https://trello.com/c/fVqebSks
Complete (Done) | Sword Animation | Animation for character swinging |  |  | KR | Easy | 9 | https://trello.com/c/5p970SYC

## Archived 3 Alpha Sprint
List | Title | Description | Points | Due | Members | Labels | Card # | Card URL
Sprint Backlog (Alpha) | [archived] Air Power | Create a tornado to knock enemies back, particle system |  |  | KR | Easy | 11 | https://trello.com/c/xtfRZqco
Sprint Backlog (Alpha) | [archived] Movement | The camera will follow the characters movement throughout the level. Should not be able to see the whole level. |  |  |  | Easy,prereq: Base Implementation of Character movement | 23 | https://trello.com/c/cuF1beHs
In progress | [archived] Title Menu | This will be the entry point of the game. Players will be able to select level, start a new game, change settings and exit. |  |  | KR | Easy,prereq: setting, level select, audio | 28 | https://trello.com/c/oX3sJHEq
Complete (Done) | [archived] Ability to pause the game | Intent: - Allow the user to stop playing the game momentarily |  |  | K | TRC Requirement | 7 | https://trello.com/c/D5M5gGvC