## 4 Beta Sprint
List | Title | Description | Points | Due | Members | Labels | Card # | Card URL
Important Notes | Milestone Review | Not having a working build pushed to the milestone builds folder of the repo before the day of the milestone review is unacceptable. - All teams must have a zipped exe build in the “Milestone builds” folder - We aren’t working on user stories during class time on the day of the milestone - We aren’t integrating the builds during class time on the day of the milestone Previous sprint review - Finalize Trello board - - All user stories in final categories - - Hours spent on all tasks entered - Discus work problems if there were any - - If a user story estimate was off why was it off? Next sprint planning - Sprint goal must be understood - User stories moved from product backlog to sprint backlog that supports the sprint goal - Test cases and task lists reviewed for all sprint user stories Story allocation - Planning poker completed for all stories - User story owners assigned for all stories - Sprint plan reviewed and accepted by CD before the end of the lab It is Highly suggested that the team perform a code freeze no later then 4 hours before the milestone needs to be submitted. Code freeze: A time where no changes whatsoever are permitted to the program's source code used to maintain ensure the quality and integrity of the build. - Before each milestone and sprint end, a final integration is needed. - - Forces an integration at a safe time - - Ensures there is time for testing and validation of the build - - Confirm sprint goals - - Peer check each other’s work |  | 2022-10-17 23:59 |  |  | 1 | https://trello.com/c/IndtLEf8
Important Notes | Team's agreed upon schedule | The team should agree upon a schedule when and where they will be meeting up outside of class time and document those times and places onto this card. |  |  |  |  | 16 | https://trello.com/c/ZyMQymQG
Important Notes | Story Line (Notes/To Review) | Young warrior/mage must set off on a quest on his coming of age day. The purpose is to prove his strength and worth to the community by bringing something of value back to the village. On the days leading up to his coming of age day, many villagers start to become gravely ill. A traveler who happened to be staying at the inn, told Silas about magic water that could cure any illness. He decides that his quest will be to locate this water and bring it back to save the village. The next morning, Silas sets off on his journey. He travels though the Jade Forest towards the Mountains of Magnus. It is said that within the mountains, lies a deep cave containing the healing water. Silas searches cave after cave with no luck. While at camp one night, he over hears a patrol of soldiers talking. Apparently some other soldiers have already found the healing water and are on the way to deliver it to the Tyrant King. Silas decides he must find those soldiers before they get back to the king. Despite encountering many patrols on the road to the castle, he is still unable to locate the patrol with the healing water. Now he must enter the royal city of Ambrose to continue his quest. Up ahead, he see's a patrol carrying a hydria (Greek vessel for carrying water) through the castle gates. Silas attempts to follow the patrol onto castle grounds but is captured. He is taken to the throne room where he comes face to face with the Tyrant King. The King, wanting to test the waters' effect, challenges Silas to a fight. After defeating the king, Silas must then defeat the soldiers and escape the royal city, taking the hydria with him. ending: Silas makes it back to his village with the healing water and saves everyone. |  |  |  | Easy | 28 | https://trello.com/c/0MGyl1Zv
Partially Complete | No warnings or errors in the code base | Intent: - Remove all warnings and errors from the product Note on estimation: - This is mostly a verification at the end of the sprint and usually needs little if any time dedicated to it unless there are currently known issues. People should be fixing warnings and errors as they develop their tasks. | 2 |  | KR | TRC Requirement | 13 | https://trello.com/c/YqUZwXI5
Partially Complete | Game can be played on any monitor/TV set | Intent: - Allow the game to be played on any monitor/TV set. This is testing for screen bounds images sizes and aspect ratios Note on Implementation: - Other that HUD layout, having canvas scaler components handling how each screen scales to fit aspect ratios is the main things that needs to be done to support this. Note on estimation: - This is mostly a verification at the end of the sprint and usually needs little if any time dedicated to it unless there are currently known issues. | 0.5 |  | AL | TRC Requirement | 2 | https://trello.com/c/9yW0JTkg
Partially Complete | Enemy Knockback [0.5] | Enemy knocked back by player attacks. | 1 |  | AL | Moderate | 43 | https://trello.com/c/0JXwNMiy
Partially Complete | Castle [0.5] | Building for final boss scene. Located after the royal city | 8 |  | L | Hard | 34 | https://trello.com/c/Qidmdxic
Partially Complete | Bug finding/Fixes [2] | Fix all bugs/get ride of all warnings. | 2 |  | KR,AL,K,L,R | Difficulty: Medium | 31 | https://trello.com/c/0aKVC6tN
Partially Complete | Save System [8] | Player will save current progress and be spawned from last point | 2 |  | R | Moderate | 38 | https://trello.com/c/6zyJDbuk
Complete (Done) | Play the game without needing to enable administrator mode | Intent: - Allow a larger user base by ensuring users do not need administrator access to the player the game after installation. Note on estimation: - This is mostly a verification at the end of the sprint and usually needs little if any time dedicated to it unless there are currently known issues. If the exe build did not ask for admin rights after saving was created on the last sprint it is unlikely that this will become an issue now. | 0.5 |  | KR | TRC Requirement | 3 | https://trello.com/c/8lnZNkc4
Complete (Done) | Installer for the game [0.5] | Intent: - Create an installer for the product to make it easier to distribute. Note on estimation: - There should be little time needed to complete this task, An hour or two. Installers will be created using an installer creator application. | 2 |  | KR | TRC Requirement | 10 | https://trello.com/c/apE5qi5i
Complete (Done) | Controls to function and be comfortable when playing the game on the WebGL build | This is only applicable if this is the intended secondary target platform. If the team is going with a different secondary platform this card can be archived. Intent: - Customize the controls to be fully usable on web builds if the game supports the web player as its target platform. | 2 |  | R | TRC Requirement,Target Platform | 6 | https://trello.com/c/Qmjm5zfj
Complete (Done) | Menu system final look and functionality | Intent: - Replace all placeholder assets with final ones - Ensure quality visuals throughout the product. | 3 |  | KR |  | 8 | https://trello.com/c/1smd0h5z
Complete (Done) | Play the game in a browser using WebGL | This is only applicable if this is the intended secondary target platform. If the team is going with a different secondary platform this card can be archived. Intent: - Get the game online and playable in a browser if the game supports the web as its target platform. - If you end up having issues with memory limits this blog post goes into the details on that a bit https://blogs.unity3d.com/2016/09/20/understanding-memory-in-unity-webgl/ | 5 |  | R | TRC Requirement,Target Platform | 7 | https://trello.com/c/57acLg9e
Complete (Done) | Display Power on HUD [3.5] | This will show the player the currently selected weapon and power on top of the mana bar. An image of the power and sword will be shown. | 0.5 |  | L | Moderate | 11 | https://trello.com/c/jm1qsyt6
Complete (Done) | Dialog / Quest System [8] | Have a simple dialog / quest system in order to guide player to next objective/location | 3 |  | R | Hard | 37 | https://trello.com/c/vvmJeTBh
Complete (Done) | Maintain a frame rate of at least 30 frames per second | Intent: - Maintain a smooth and clear game experience Note on estimation: - This is mostly a verification at the end of the sprint and usually needs little if any time dedicated to it unless there are currently known issues. If however the game is already having issues with framerate at the point of estimating this card then the team should make their best judgement on the time to optimize where they think the slowdowns are located. | 0.5 |  | AL | TRC Requirement | 4 | https://trello.com/c/Zw29XV4O
Complete (Done) | Wizard Boss [5] | The wizard boss fight and all it's functionalities. | 5 |  | L | yellow | 39 | https://trello.com/c/jYYcaFqg
Complete (Done) | AI Aggro Zone/Distance [0.5] | This will be the zone where the enemy will start attacking the player. If not within range the enemy will follow and idle path. | 0.5 |  | K | Moderate | 21 | https://trello.com/c/LBIIldpb
Complete (Done) | Background images | Images/Assets that will be used or created for level enemies. | 0.5 |  |  | Easy | 12 | https://trello.com/c/W7vLVJwy
Complete (Done) | AI patrol pathing [4] | Path the enemy will follow when player is not within their sight. Random path movement to add a challenge and less predictability. | 2 |  | K | Moderate | 20 | https://trello.com/c/acmDS62F
Complete (Done) | Credits (everyone who contributed to creating the game to get credit for their work) | Intent: - Credit everyone who contributed to the product - For outsourced assets from web portals give enough information to be able to find the source of the asset (“Asset Name by AuthorName from website.com”) Note on estimation: - Time to complete this task is heavily dependent on if we have been maintaining a list of where we got our assets from or if we need to spend time to re-find the source of the assets. | 0.5 |  | KR | TRC Requirement | 11 | https://trello.com/c/OakPlWPP
Complete (Done) | Cave Music [1.5] | Background music that the player will hear when they enter the caves. | 1 |  | K | Easy | 10 | https://trello.com/c/hgPB3rCo
Complete (Done) | Village Music [1.5] | Background music that the player will hear when they enter the village | 1 |  | K | Easy | 9 | https://trello.com/c/6kvezCNV
Complete (Done) | Attack animation [2] | Enemy attack animation. This will be a way the player will know when the enemy is about to attack | 2 |  | KR | Easy | 22 | https://trello.com/c/URXgLv2Y
Complete (Done) | Wandering Music [1.5] | Music that plays in the background when the player is traversing the world. | 1 |  | K | Easy | 8 | https://trello.com/c/xeUEYfeZ
Complete (Done) | City Music [1.5] | Background music that the player will hear when they enter the city | 1 |  | K | Easy | 40 | https://trello.com/c/p39nEgBz
Complete (Done) | MiniMap [3] | HUD map that shows surrounding terrain, player position and the location of the next quest. | 3 |  | KR | Moderate,Prereq: Quest system | 32 | https://trello.com/c/G3r6xgOG
Complete (Done) | Missions/tasks [8] | These are the quests: Get through the forest Search caves in the mountains Follow enemy patrols enter royal city enter the castle fight boss escape royal city | 5 |  | R | Easy | 2 | https://trello.com/c/ge8sjaeD
Complete (Done) | Identifiable icon | Intent: - Allow users to easily recognize the game from its icon image Note on estimation: - There should be very little time needed to complete this task. Adding an icon tot he game's exe using unity involves a drag and drop in the player settings. | 0.5 |  | K | TRC Requirement | 9 | https://trello.com/c/hmeinkN1
Complete (Done) | Setting Menu [8] | Menu where you can change video settings, audio settings and can change key bindings. | 2 |  | KR | Easy | 6 | https://trello.com/c/AaorDQyc
Complete (Done) | Healing Spell [0.5] | Spell that heals the player | 0.5 |  | L | Easy | 17 | https://trello.com/c/7nUJLvIK
Complete (Done) | Experience the game without needing to have an additional player [0.5] | Intent: - Ensure all players can experience a portion of the game without the need of an additional player on an online connection. Note on estimation: - This is mostly a verification at the end of the sprint and needs little if any time dedicated to it. If an entire new mode needs to be created to support this then there should be other cards defining that mode. | 0.5 |  | KR | TRC Requirement | 5 | https://trello.com/c/eiJM6YQG
Complete (Done) | Tornado/Gust | Main attack that the soldiers will be able to cast. | 2 |  | KR | Hard,prereq: Knockback,prereq: Volantes Inimicus | 3 | https://trello.com/c/O30Dg3gv
Complete (Done) | Enemy drop on death [0.5] | Intent: - Enemies sometimes dropping useful items when killed: Health and Mana | 1 |  | KR | Easy | 25 | https://trello.com/c/RrismlOj
Complete (Done) | Collectable Pick up | Intent: - An item that adds a collectable item to the player's inventory when picked up -Magic Water | 2 |  | AL | Easy | 24 | https://trello.com/c/pl5p9nna
Complete (Done) | Leveling System [2] | Intent: Add experience and leveling up system for the player. | 2 |  | AL | Easy | 45 | https://trello.com/c/KxcPfvCr
Complete (Done) | Effect: Bleed [3] | Intent: - A visual effect to provide feedback to the player that the enemy was damaged. | 2 |  | AL | Easy | 26 | https://trello.com/c/bhEK0sMD
Complete (Done) | Transition from Forest to caves [0.5] | Transition point to go from main level to caves | 1 |  | KR,AL | Easy | 29 | https://trello.com/c/QutRItSj
Complete (Done) | NPC's | peaceful npc's in village and royal city optional: should they say something if player tries to speak to them? Could be written in actual Latin letters or English | 0.5 |  | AL | Moderate | 19 | https://trello.com/c/s1vAGF0V
Complete (Done) | Debug tools removal [0.5] | Intent: - Finalizing the build to prepare for the quality assurance and submission process. Note on estimation: - Usually all this involves is commenting out the lines that trigger the debug functionality. This is mostly a verification at the end of the sprint and usually needs little if any time dedicated to it unless there are currently known issues. | 1 |  | AL |  | 12 | https://trello.com/c/XczERGnQ
Complete (Done) | Enemy particle system for spells [5] | Enemy spells that the enemy will cast. Spells are Fire, ice, lightning and tornado | 5 |  | KR | Difficulty: Medium | 30 | https://trello.com/c/Ita0qLAT
Complete (Done) | Mana Regeneration [0.5] | Add time delayed mana regeneration to player | 0.5 |  | AL | Easy | 42 | https://trello.com/c/m2RdsgIo
Complete (Done) | Royal City [1] | The royal city outside the castle | 2 |  | AL | Easy | 44 | https://trello.com/c/DWrMUmoy
Complete (Done) | Forest [3] | The main level the player will interact with to get from point to point. | 3 |  | AL | Easy | 13 | https://trello.com/c/icp5BZT0
Complete (Done) | Player Spawn Points [2] | Player spawn point/checkpoints that updates as the player traverses through the terrain. Village point Forest point Cave points Castle point | 2 |  | AL | Easy | 4 | https://trello.com/c/MfF81SJu
Complete (Done) | Mana Pick up [0.5] | Intent: - An item that adds mana to the player's mana pool when picked up | 0.5 |  | AL | Easy | 23 | https://trello.com/c/lEItPp0I
Complete (Done) | Cave2 [3] | Second cave the player encounters. Wolf den | 3 |  | AL | Easy,prereq: background images | 14 | https://trello.com/c/tG7hM8oW
Complete (Done) | Cave3 [3] | Third cave the player encounters. Bandits den | 3 |  | KR,AL | Easy,prereq: background images | 15 | https://trello.com/c/SU2XqSap

## Archived 4 Beta Sprint
List | Title | Description | Points | Due | Members | Labels | Card # | Card URL
Sprint Backlog (Beta) | [archived] Play the game using an android device | This is only applicable if this is the intended secondary target platform. If the team is going with a different secondary platform this card can be archived. Intent: - Make the game playable on an android tablet If the game supports the tablet as its target platform. - If you have not already installed the packages necessary to export android build you can follow the directions how to do so here https://www.youtube.com/watch?v=4YNH9Y7NR3U |  |  |  | TRC Requirement,Target Platform | 14 | https://trello.com/c/kAiJCld2
Sprint Backlog (Beta) | [archived] Controls function and be comfortable when playing the game on an android device | This is only applicable if this is the intended secondary target platform. If the team is going with a different secondary platform this card can be archived. Intent: - Customize the player controls for a touch-based device if the game supports the tablet as its target platform. |  |  |  | TRC Requirement,Target Platform | 15 | https://trello.com/c/9WcUS8w8
Sprint Backlog (Beta) | [archived] Spell crafting | The ability to collect, spend and manage points that then allow for the crafting of individual spells which are added to the spell inventory list. | 5 |  | L | Difficulty: Medium | 1 | https://trello.com/c/O3SBlo1m
Sprint Backlog (Beta) | [archived] Dialogue Box for story | Intent: Create a familiar presentation for the player to interact with dialogue and prompts. | 3 |  | R | Moderate | 5 | https://trello.com/c/GimwSfS4
Sprint Backlog (Beta) | [archived] Video Mode | Change between window, borderless, and fullscreen | 1 |  | KR | Moderate | 7 | https://trello.com/c/A8fAM1pH
Sprint Backlog (Beta) | [archived] Shops | Item shops for the player to purchase game items. | 5 |  | R | Moderate | 16 | https://trello.com/c/T7y3dbiz
Sprint Backlog (Beta) | [archived] Boss, Cave1 | This will be the boss in the caves | 2 |  | K | Easy | 33 | https://trello.com/c/whtfZVhv
Sprint Backlog (Beta) | [archived] Soldier (Ranged) | Enemy - Ranged Soldier that uses magic | 2 |  | KR | Moderate,Prereq: Powers | 36 | https://trello.com/c/TgeEsgTs
In progress | [archived] Eversor (Final Boss, Tyrant King) | This is the final boss of the game and will be in the players home universe. The boss will have all the powers that the previous universe had. Will be the hardest boss. | 2 |  | L | Hard | 18 | https://trello.com/c/P5uIAAAn
Partially Complete | [archived] Bandit (Ranged) | Enemy - Ranged Bandit that uses magic | 2 |  | KR | Moderate,Prereq: Powers | 35 | https://trello.com/c/33z0bWW7
Partially Complete | [archived] Soldier (Ranged) | Enemy - Ranged Soldier that uses magic | 2 |  | KR | Moderate,Prereq: Powers | 41 | https://trello.com/c/dcmHFjU9