## 5 QA (Equei Iter)
List | Title | Description | Points | Due | Members | Labels | Card # | Card URL
Can Not Reproduce [Waiting Confirmation] | In some areas the terrain prevents you from picking up the health potions. | Steps to reproduce: - have an enemy or boss drop an item -see where it falls -attempt to pick it up What was seen: - item falls all the way through terrain and is unreachable - item falls partially through the terrain and cannot be picked up Expected results: - items should be able to be picked up |  |  | JH,AL | Moderate | 22 | https://trello.com/c/n4LK9gIu
Can Not Reproduce [Waiting Confirmation] | When you restart in the spider cave, not after death it resets everything. | I fell through the map when I attacked the boss spider. Tried to restart, it sent me back to the beginning of the cave, but reset all progress. Steps to reproduce: -Attack the boss spider What was seen: -I fell through the map -Had to restart everything Expected Results: -Shouldn't be able to fall through the terrain -Should be a respawn |  |  | JH | A - Crash/ShowStopper | 51 | https://trello.com/c/641NyMDB
Fixed [Waiting Confirmation] | Player doesn't know what to do when approaching a person they can speak to. | Upon pressing "e" it triggers the conversation, but if a player doesn't know to try pressing e, they will be confused. Visual feedback only showed up at the end of the game, once you come back to the village. |  |  | JL,R | C - Minor | 17 | https://trello.com/c/b1TNEqa7
Fixed [Waiting Confirmation] | Text repeats at Patrol Boss | When the player completes the cave with the patrol boss, some of the text repeats at the end. Steps to reproduce: - talk to the cave patrol boss What was seen: - text repeats Expected results: - only see text once |  |  | JH,R | C - Minor | 21 | https://trello.com/c/v6FrXQxt
Fixed [Waiting Confirmation] | Leaving royal city text |  |  |  | R | D - Suggestion | 37 | https://trello.com/c/YDakIwXv
Fixed [Waiting Confirmation] | Loading a save after restart loads from before restart, and gives start dialog again. | Steps to reproduce - 1 Start game - 2 make some progress - 3 save game - 4 restart - 5 click through dialog - 6 load What was seen: - Loading after restarting will load old save and shows starting dialogue what was expected - no loading after restart |  |  | NB,R | C - Minor | 52 | https://trello.com/c/qAgQrJKU
Fixed [Waiting Confirmation] | Tornado spell does not work | When you pick up the tornado spellbook at the end of the spider level you no longer have the tornado spell and the staff doesn't work. Steps to reproduce: - beat spider boss - pick up spell book - leave the cave What was seen: - staff no longer works - UI does not change when switching Expected results: - the ability should stay |  |  | JH,R | Moderate | 27 | https://trello.com/c/Py0kF9C3
Fixed [Waiting Confirmation] | Loading on start menu leaves you stuck | Steps to reproduce: - 1 Save game - 2 Load game - 3 Press esc again to become unstuck What was seen: - After loading form the menu, player could not move Expected results: - Load and be able to move |  |  | JL,R | B - Critical | 43 | https://trello.com/c/uugGvjdI
Fixed [Waiting Confirmation] | Text repeats at Wizard King first interaction | Steps to reproduce: - enter the area with the wizard king What was seen: - text repeated Expected results: - text should only play once |  |  | RR,R | C - Minor | 25 | https://trello.com/c/ZiDFHS8Q
Fixed [Waiting Confirmation] | Several misspelled words when speaking to the Village elder [0] | Steps to reproduce:: -talk to the village elder What was seen: - the word spring is spelled wrong - "It will be a treacherous journey that would be worth for your coming of age" -"Village editor" Expected results: - spring is spelled correctly - the second one should say "worthy" not "worth" -is the village editor title supposed to say village elder? |  |  | AL | D - Suggestion | 18 | https://trello.com/c/QKWDBykS
Fixed [Waiting Confirmation] | Player can climb the mountain on opposite side of castle/city area. [0.5] | The player can climb the mountain and fall through the map. Too many out-of-bounds spots that need to be resolved so player can't fall off the terrain. Steps to reproduce: - walk to the side of a mountain - walk straight up the mountain - jump off the side What was seen: - player can fall forever outside the bounds of the map Expected results: - either an invisible wall or terrain too steep to walk up | 0 |  | JH,KR | B - Critical | 19 | https://trello.com/c/4mRMUhi3
Fixed [Waiting Confirmation] | When you die from attacks and respawn, you sometimes take damage. [0] | I think the game may not be pausing properly on the death menu. Steps to reproduce: -Die -respawn What was seen: -damage was taken Expected results: - respawn at full health | 0 |  | JH,KR | C - Minor | 15 | https://trello.com/c/9fGaQuCf
Fixed [Waiting Confirmation] | Player can't switch weapons until fireball is destroyed. [0.5] | Steps to reproduce: - 1 Start game - 2 Switch weapon to fireball - 3 Fire projectile - 4 attempt to switch back to melee What was seen: - player unable to switch back to melee until fireball is destroyed Expected results: - player switches between on button press | 0.5 |  | RR,KR | C - Minor | 5 | https://trello.com/c/sxPxOVqY
Fixed [Waiting Confirmation] | Wolf enemy attacks deal damage when not near or facing player. [0.5] | Steps to reproduce: - 1 after game start go south until wolf enemies - 2 run out of range and wait for wolf to attack what was seen: - wolves can damage player from a far distance - wolves can damage player while facing away expected results - wolves dealing damage when within melee range | 0.5 |  | NB,KR | B - Critical | 9 | https://trello.com/c/IFGuZnuC
Fixed [Waiting Confirmation] | Swordsman in the castle [0] | Steps to reproduce: - 1 Complete questline up to the fight against the wizard - 2 Swordsman enemy is walking through/underneath the floor - 3 What was seen: - Had to attempt to hit him so he could enter the castle through the floor. Expected results: - Enemy is on the castle grounds. | 0 |  | RR,KR | C - Minor | 50 | https://trello.com/c/NU1zWyWc
Fixed [Waiting Confirmation] | Blue potion icon on UI [2] | Steps to reproduce: - 1 Start game - 2 - 3 What was seen: - Blue potion in UI that did not change at all throughout game Expected results: - It was mana perhaps? Magic did not deplete it | 0.5 |  | RR,AL,KR | C - Minor | 42 | https://trello.com/c/jdXg0oXm
Fixed [Waiting Confirmation] | Camera inside cave follows player too low [0] | Steps to reproduce: after game start after leaving forest -1 go down the right path to the spider cave -2 enter cave what was seen: - upon entering, the camera drops almost to the floor making traversal difficult (also clips through floor) what was expected: - normal camera follow behaviour | 0 |  | NB,KR | C - Minor | 13 | https://trello.com/c/jP8FmeVb
Fixed [Waiting Confirmation] | Largest house on the farthest south side of main village is able to be clipped through. [0.5] | Steps to reproduce: -1 start new game -2 go to the southern most part of village to the large house What was seen: - northern part of house can be walked through - from inside, the player doesn't stay on the house floor / clips through floor What was expected: - being properly blocked by walls/floors | 0.5 |  | JH,AL | C - Minor | 8 | https://trello.com/c/G1yQ04AE
Fixed [Waiting Confirmation] | Press B and go back to last save [0] | Steps to reproduce: - make progress in the game after seeing the autosave - press B What was seen: - character teleports back to point of autosave Expected results: - character should not teleport back to a previous spot | 0 |  | RR,KR | B - Critical | 28 | https://trello.com/c/vCDWw4be
Fixed [Waiting Confirmation] | Walking up steep terrain [0] | Steps to reproduce: - walk up terrain that seems to be too steep What was seen: - was able to get to areas out of order (like the final castel) and skip some of the game Expected results: - should not be able to run up overly steep walls | 0 |  | JL,KR | Moderate | 39 | https://trello.com/c/T8FGKZzo
Fixed [Waiting Confirmation] | Floating house [0.5] | Steps to reproduce: - leave spawning village to the south/southwest - look to the house on the right side of the path What was seen: - House was floating above most of the terrain - inside house there was terrain clipping through the floor Expected results: - house is not floating -house is properly floored |  |  | RR,AL | C - Minor | 33 | https://trello.com/c/KJsjgrPJ
Fixed [Waiting Confirmation] | Water terrain is not connected to the ground [0.5] | Steps to reproduce: - leave the village to the southwest and go to the bridge -jump onto the water and head west What was seen: - before you hit the boat you will see a layer of water floating higher than the rest -you will also see terrain and trees underneath where the water should be Expected results: - continuous water |  |  | RR,AL | Moderate | 29 | https://trello.com/c/QYSOgbyc
Fixed [Waiting Confirmation] | Small spiders do no damage on path. [1] | Steps to reproduce: - Walk up to the small spiders What was seen: - Small spiders not attacking even though they are chasing Expected results: - Small spiders attack | 0.5 |  | JL,KR | B - Critical | 44 | https://trello.com/c/L25pX9iC
Fixed [Waiting Confirmation] | Royal Village is above terrain [2] | Steps to reproduce: - go to royal village - view the bottom of the city What was seen: - royal city is floating above the terrain Expected results: - Royal city should be flat with the terrain |  |  | RR,AL | C - Minor | 34 | https://trello.com/c/FMduk9RH
Fixed [Waiting Confirmation] | Items floating in house (tables invisible?) [0.5] | Steps to reproduce: -1 start game -2 face south and go to house closest to river -3 enter house What was seen: -objects appear to be floating in air inside the house. Expected results: - table holding objects or objects properly sitting on floor. |  |  | NB,AL | C - Minor | 7 | https://trello.com/c/9eKUz2Lz
Fixed [Waiting Confirmation] | Enemies would drop a blue potion that could not be picked up [0.5] | Steps to reproduce: - 1 Kill enemies/noticed during dungeon with swordsmen - 2 - 3 What was seen: - Blue potion dropped Expected results: - Refill mana perhaps? |  |  | RR,AL | D - Suggestion | 40 | https://trello.com/c/hOWa97Nb
Fixed [Waiting Confirmation] | Attacks on enemies don't land all the time. [1] | Steps to reproduce: after game start -1 follow the road out of town until spider enemies - 2 try to attack what was seen: - spider enemies are only taking damage occasionally - hit boxes too small? - Enemies change locations on damage what was expected: - Enemies in front of player take damage when attacked | 0.5 |  | NB,KR | B - Critical | 12 | https://trello.com/c/77nwVPl8
Fixed [Waiting Confirmation] | Enemy attacks causes them to immediately change position [0] | Steps to reproduce: after game start -1 travel south until wolf enemies -1 attack a wolf what was seen: - on taking damage, wolf immediately changes location a small distance away expected: - animation plays without moving enemy | 0 |  | NB,KR | B - Critical | 10 | https://trello.com/c/kKQ7PFcG
Fixed [Waiting Confirmation] | Wolves would be stuck together in their spawner [1] | Steps to reproduce: - 1 After starting game, head to bridge - 2 Wolves spawn stuck together - 3 They become unstuck after hitting/approaching them What was seen: - One single wolf with 3 heads, 3 tails Expected results: - 3 separate enemies | 1 |  | RR,KR | C - Minor | 35 | https://trello.com/c/0Cg9IgYy
Fixed [Waiting Confirmation] | Player can walk through closed doors in the village [0.5] | Steps to reproduce: - 1 Start the game. - 2 Walk/jump to get inside houses with closed doors. - 3 What was seen: - Can get inside ones with closed doors. Expected results: - Can't walk through closed doors. |  |  | JL,AL | C - Minor | 48 | https://trello.com/c/Dz0fOmK3
Fixed [Waiting Confirmation] | Friendly AI should either have a larger range or slower movement. |  |  |  | JH,AL | D - Suggestion | 16 | https://trello.com/c/xaHuJr0Y
Fixed [Waiting Confirmation] | Houses/Buildings are not baked properly, [0.5] | Steps to reproduce: - 1 Walk through the houses What was seen: - 1 All AI can walk through buildings in their pathway - 2 Some of the enemies get stuck in the terrain. Expected results: - Be able to walk close to buildings, not through them. | 0.5 |  | NB,AL,KR | A - Crash/ShowStopper | 46 | https://trello.com/c/Gg5fngFy
Fixed [Waiting Confirmation] | Enemies show still on map after dead [0] | Steps to reproduce: - 1 Killing enemies - 2 - 3 What was seen: - All through the game Expected results: - Perhaps change the color of them on death on map? |  |  | RR,AL | D - Suggestion | 32 | https://trello.com/c/O0MftAEH
Fixed [Waiting Confirmation] | Camera collides with objects [0] | Steps to reproduce: - allow an NPC to walk behind the character - try and move the player character in front of an object What was seen: - The camera will zoom in on the player character unnecessarily Expected results: - camera should stay at same distance from the character | 0 |  | JL,KR | C - Minor | 47 | https://trello.com/c/pUn4AlZd
Fixed [Waiting Confirmation] | Player can't go up stairs into houses. [0] | Steps to reproduce: After game start - 1 Try to walk up stairs into raised house. What was seen: - player gets stuck and has to jump over stairs What was expected: - player walks up stairs into house |  |  | NB,AL | C - Minor | 6 | https://trello.com/c/0AIWlahO
Fixed [Waiting Confirmation] | No resolution for 5120x1440 [0.5] | resolution does not scale to an appropriate size. No way to change resolution. Had to play on a different monitor. Steps to reproduce: - open game on a 5120x1440 monitor What was seen: - resolution was stretched to where I could not see or select all the menu options Expected results: - game should scale correctly | 0.5 |  | RR,KR | Moderate | 30 | https://trello.com/c/zLaNI9Vj
Fixed [Waiting Confirmation] | Player can't pick up the potion in level 3? easily. [0.5] |  |  |  | JH,AL | D - Suggestion | 20 | https://trello.com/c/xW0reGbD
Fixed [Waiting Confirmation] | Door animation in village [0.5] | Door on building attached to animal pen will close when you walk through it and look closed when the camera is behind you. When you turn around the door shows as open. When you walk back out an animation plays to open the door Steps to reproduce: - walk through the door of the house in the animal pen -rotate camera What was seen: - door is not properly closed Expected results: - door should be closed |  |  | JH,AL | C - Minor | 31 | https://trello.com/c/o3QBuPjf
Fixed [Waiting Confirmation] | Wizard King is partially under terrain. [0] | Steps to reproduce: - go to the wizard king castle What was seen: - wizard was stuck in the floor of the castle Expected results: - wizard is not stuck | 0 |  | JH,KR | A - Crash/ShowStopper | 23 | https://trello.com/c/3sQa4nDe
Fixed [Waiting Confirmation] | Fireball projectile going through walls | Steps to reproduce: - 1 Change weapon - 2 Press to shoot a projectile against the wall - 3 Wait until animation is done to attack again What was seen: - Fireball goes through walls Expected results: - Fireball/projectile colliding with walls |  |  | JL,L | C - Minor | 38 | https://trello.com/c/OYSF0AqP
Fixed [Waiting Confirmation] | Cannot complete the questline [0.5] | Steps to reproduce: -Start the game -Complete the quests -Go back to village What was seen: -Never was able to finish the Save the Village even though all quests were complete. (See attached photo) Expected results: - Complete the game | 1 |  | JH,KR | A - Crash/ShowStopper | 41 | https://trello.com/c/Ux0D4cTg
Duplicate | Floating House | Steps to reproduce: - in spawning village go to the back west (house with swords and shields in it) -look underneath the house -also look at the house next to it What was seen: - house was floating above the terrain Expected results: - house should be level with the terrain |  |  | JL | C - Minor | 49 | https://trello.com/c/kDTc0s4n
Duplicate | NPCs walk through walls | Steps to reproduce: - 1 Start on the village, watch the animals - 2 Go to the city, watch the NPCs - 3 What was seen: - NPC walking through walls Expected results: - NPCs colliding with their surrounding properly |  |  | JL | C - Minor | 45 | https://trello.com/c/uuj6K0KL
Not a bug | When quest list is longer than 6 you can no longer see the other quests. | Steps to reproduce: - acquire more than 6 quests What was seen: - could no longer see additional quests Expected results: - should be able to scroll quests |  |  | RR,R | Moderate | 24 | https://trello.com/c/TLDezn8F
Not a bug | Exiting spider cave spawns player away from cave | Steps to reproduce: after game start after leaving forest -1 enter spider cave -2 make way through cave to exit what was seen: - upon exiting the cave, the player was spawned down the road, away from the mountains / cave what was expected: - spawning next to cave entrance or separate cave exit |  |  | NB | C - Minor | 14 | https://trello.com/c/Az0bDDvR
Known Shippable | Can walk on water | I don't know if this is a feature or a bug but water may want to be added to the level |  |  |  | D - Suggestion | 26 | https://trello.com/c/9zsmNVK5
Known Shippable | Walking animation in air [0.5] | Steps to reproduce: - jump off a high point -continue to move forward What was seen: - player continues walking animation Expected results: - either no animation or a falling animation |  |  | JL,AL | C - Minor | 36 | https://trello.com/c/qpPZMUSB
Known Shippable | Compass does not display correct directions | Steps to reproduce after game start -1 face south -2 turn 180 degrees what was seen - it seems the player and compass are both rotating, causing a full 180 degree turn to end up facing the same direction (ie turning 180 degrees from south, player will appear to be facing south still what was expected - only 1 rotates, compass or player, not both (maybe give an option to select?) |  |  | NB | B - Critical | 11 | https://trello.com/c/BIl1jS3G

## Archived 5 QA (Equei Iter)
List | Title | Description | Points | Due | Members | Labels | Card # | Card URL
Open | [archived] Bug Formatting Example <Description Here> | Steps to reproduce: - 1 - 2 - 3 What was seen: - <Seen> Expected results: - <Expected> |  |  |  |  | 1 | https://trello.com/c/M4eAsMqO
Open | [archived] Bug Formatting Example <Description Here> | Steps to reproduce: - 1 - 2 - 3 What was seen: - <Seen> Expected results: - <Expected> |  |  |  |  | 2 | https://trello.com/c/N9um7MU2
In Progress | [archived] Wizard Boss [5] | The wizard boss fight and all it's functionalities. | 5 |  | L | yellow | 1 | https://trello.com/c/CQPSkpwe
In Progress | [archived] Castle [0.5] | Building for final boss scene. Located after the royal city | 8 |  | L | Hard | 2 | https://trello.com/c/CKusY73d
In Progress | [archived] Save System [8] | Player will save current progress and be spawned from last point | 2 |  | R | Moderate | 3 | https://trello.com/c/s4tXYTA9
In Progress | [archived] No warnings or errors in the code base | Intent: - Remove all warnings and errors from the product Note on estimation: - This is mostly a verification at the end of the sprint and usually needs little if any time dedicated to it unless there are currently known issues. People should be fixing warnings and errors as they develop their tasks. | 2 |  | KR | TRC Requirement | 4 | https://trello.com/c/9je1svq7